## How to Use
How to Use This Workbook
1 | Dropdown cells are shaded light blue. Click a blue cell, then use the small dropdown arrow that appears.
2 | Dropdown values are stored on the visible Dropdown Lists sheet and can be edited by L&D program owners.
3 | Formula cells are shaded light green and calculate team/pod counts or KPI achievement automatically.
4 | Use Learning Objectives to select what is in scope for each program, then connect those objectives to metrics and owners.
5 | Use Cohort Planning to model regional/global cohorts, teams, pods, mobs, triads, and pairs.
Sheet Colors Legend
Dark Blue | Program Planning
Teal | Prioritization, Communication and Process
Green | Examples with Example Data
Purple | Delivery, Metrics

## Operating Model
Category | Details
L&D Operating Model Type | Global Enterprise Learning Design
Program Type | Technical Software Engineering Enablement
Primary Focus | GitHub Copilot + Full Stack Application Development
Target Audience | Software Engineers
Delivery Model | Global Cohort-Based Learning
Scaling Strategy | Teams, Pods, Mobs, Triads, Pairs
Governance Model
Program Management Structure
Learning Design Standards

## Program Blueprint
Program Details | Description
Program Name | AI Software Intern Challenge
Program Description
Program Goals
Program Start Date | 2026-06-01
Program End Date | 2026-07-31
Program Duration | 12 Weeks
Global Regions | Global
Languages
Cohort Count

## Learning Objectives
Objective Category | Objective | Included | Priority | Measurement Method | Owner
Technical | Accelerate AI-assisted software engineering | Yes | Must Have | Mixed Methods | Engineering Lead
Technical | Improve engineering collaboration | Yes | Must Have | Peer Review | Facilitator Lead
Business | Increase delivery velocity | Optional | Could Have | Dashboard KPI | Engineering Lead
Technical | Improve code quality | Yes | Should Have | GitHub Metrics | Engineering Lead
Learning | Use GitHub Copilot to understand code bases | Yes | Must Have | Assessment | Facilitator Lead
Learning | Generate unit and integration tests with AI | Yes | Should Have | Capstone Rubric | Facilitator Lead
Learning | Perform AI-assisted code reviews | Yes | Should Have | Mixed Methods | Facilitator Lead
Learning | Generate new code using AI pair programming | Regional Only | Should Have | Capstone Rubric | Curriculum Lead
Business | Collaborate effectively in pods and teams | Yes | Must Have | Peer Review | Facilitator Lead
Business | Individual Ownership in Learning | Yes | Must Have | Mixed Methods | Curriculum Lead
Business | Team Engagement in Learning | Yes | Must Have | Mixed Methods | Curriculum Lead
Technical | Metrics for Firm Tool Stack Optimized | Yes | Should Have | Dashboard KPI | Engineering Lead
Note on C1: Dropdown: Yes, No, Phase 2, Optional, Regional Only, Pilot Only
Note on D1: Dropdown: MoSCoW priority options.

## Learner Structures
Structure Type | Recommended Size | Purpose | Notes | Included
Global Cohort | 100-500+ | Enterprise-wide learning alignment |  | Yes
Regional Cohort | 25-200 | Regional coordination |  | Yes
Team | 10 or less | Delivery team collaboration |  | Yes
Pod | 3-6 | Focused coding collaboration |  | Yes
Mob | 5-12 | Collaborative swarm coding/problem solving |  | Yes
Triad | 3 | Peer coaching/review |  | Yes
Pair | 2 | AI pair programming |  | Yes
Select...
Structure | Purpose | Example Usage
Cohort | Shared learning journey | Weekly demos and workshops
Teams | Deliver real outcomes | Build full-stack applications
Pods | Focused collaboration | Frontend/backend subgroups
Pairs | Skill-building and feedback | Pair programming with Copilot
Triads | Reflection and coaching | Code review exercises
Mobs | Collective problem solving | Debugging and architecture sessions

## 12 Week Plan
Week | Primary Activity | Primary Learner Structure
1 | Cohort kickoff + team formation | Regional Cohort
2 | Pair programming fundamentals | Team
3 | Pod architecture planning | Pod
4 | Triad code review workshops | Triad
5 | Team sprint execution | Team
6 | Cohort midpoint demos | Team
7 | Mob debugging session | Mob
8 | Advanced Copilot workflows | Pod
9 | Pair refactoring exercises | Pair
10 | Triad presentation practice | Triad
11 | Team stabilization sprint | Team
12 | Cohort showcase and retrospective | Regional Cohort

## Cohort Planning
Cohort | Region | Learner Count | Recommended Team Count | Recommended Pod Count | Facilitators | Start Date | End Date | Primary Learner Structure
Q3-2026-INT | NAMR | 250 | 25 | 50 | 10 |  |  | Pod
Q3-2026-INT | LATAM | 48 | 5 | 10 | 2 |  |  | Pod
Q3-2026-INT | EMEA | 125 | 13 | 25 | 5 | ` |  | Pod
Q3-2026-INT | INDIA | 400 | 40 | 80 | 16 |  |  | Pod
Q3-2026-INT | APAC | 25 | 3 | 5 | 1 |  |  | Pod
| Select... | [6 empty] | Select...

## Learning Journey Map
Phase | Learner Experience | Facilitator Activities | Deliverables
Pre-Work
Kickoff
AI Foundations
Code Base Exploration
Testing with AI
Code Review Practice
New Code Generation
Capstone Delivery
Assessment & Reflection

## Learning Journey Map Ex
Phase | Learner Experience | Facilitator Activities | Deliverables
Pre-Work | Complete AI readiness assessment and GitHub Copilot setup | Validate platform access, distribute onboarding communications, monitor readiness | Completed readiness survey, platform access confirmed
Kickoff | Join cohort kickoff and form Teams/Pods | Facilitate orientation session and team formation | Team assignments, pod rosters, collaboration charter
AI Foundations | Learn prompting techniques and Copilot workflows | Demonstrate prompting strategies and AI engineering patterns | Prompt library, AI usage guidelines
Code Base Exploration | Use Copilot to understand full stack application architecture | Guide learners through repo walkthroughs and architecture discussions | Architecture summaries, code exploration notes
Testing with AI | Generate unit and integration tests using Copilot | Coach learners on testing patterns and AI-assisted validation | Test suites, coverage reports
Code Review Practice | Conduct AI-assisted peer code reviews in Pods/Triads | Facilitate review sessions and quality calibration | Code review checklists, feedback logs
Pair Programming | Work in Pairs/Triads to generate and refactor code | Observe collaboration patterns and provide coaching | Pull requests, refactored code samples
Mob Programming Session | Participate in Mob problem-solving exercise | Moderate mob sessions and reinforce engineering practices | Shared solutions, decision logs
Capstone Sprint | Deliver production-ready application enhancement | Support sprint reviews and technical coaching | Working application features, sprint demo
Assessment & Reflection | Reflect on AI engineering practices and collaboration | Conduct retrospectives and assess outcomes | Skills assessments, retrospective summaries
Reinforcement | Continue applying AI workflows on-the-job | Provide office hours and follow-up coaching | Adoption metrics, continued learning plans

## RACI Matrix
Activity | Program Mgmt | Learning Design | Facilitators | Engineering Leads | Operations | Executives
Program Strategy | Select... | Select... | Select... | Select... | Select... | Select...
Curriculum Design | Select... | Select... | Select... | Select... | Select... | Select...
Facilitator Readiness | Select... | Select... | Select... | Select... | Select... | Select...
Platform Setup | Select... | Select... | Select... | Select... | Select... | Select...
Assessment Strategy | Select... | Select... | Select... | Select... | Select... | Select...
Metrics & Reporting | Select... | Select... | Select... | Select... | Select... | Select...
Engineer Learning Ownership | Select... | Select... | Select... | Select... | Select... | Select...
Engineer Learning Retention | Select... | Select... | Select... | Select... | Select... | Select...
Post Program Application | Select... | Select... | Select... | Select... | Select... | Select...

## MoSCoW Prioritization
Category | Requirement | Priority | Owner
Tech Team | GitHub Copilot access | Must Have | Engineering Lead
Tech Team | Full stack application repository | Must Have | Curriculum Lead
Program Management | Pod collaboration structure | Must Have | Program Manager
Program Delivery Team | Regional facilitators | Select... | Facilitator Lead
Curriculum Team | Gamification | Select... | Curriculum Lead
Curriculum Team | Custom platform development | Select... | Curriculum Lead
Tech Team |  | Select... | Select...
Tech Team |  | Select... | Select...
Tech Team |  | Select... | Select...
Tech Team |  | Select... | Select...

## Communication Plan
Audience | Communication Type | Cadence | Channel | Owner
Participants | Program Updates | Kick Off | Teams/Slack | Select...
Managers | Progress Reports | Daily | Email | Program Manager
Executives | KPI Dashboard | Weekly | Email | Executive Sponsor
Facilitators | Facilitator Sync | Daily | Teams/Slack | Facilitator Lead
Regional Leads | Regional Coordination | Weekly | Teams/Slack | Regional Lead
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...
Select... |  | Select... | Select... | Select...

## Facilitator Guides
Session | Facilitator Guidance | Materials Needed | Timing
Kickoff |  |  | Select...
AI Coding Workshop |  |  | Select...
Code Review Workshop |  |  | Select...
Testing Workshop |  |  | Select...
Mob Programming Session |  |  | Select...
Capstone Review |  |  | Select...

## Facilitator Guides Ex
Session | Facilitator Guidance | Materials Needed | Timing | Team Makeup
Kickoff Session | Introduce program goals, explain collaboration structures (Teams, Pods, Pairs), establish working agreements, and review GitHub Copilot expectations. Facilitate icebreaker and pod formation activities. | Slide deck, cohort roster, collaboration charter template, onboarding checklist | 90 min | Regional Cohort
GitHub Copilot Foundations | Demonstrate effective prompt engineering techniques, explain AI-assisted development workflows, and guide learners through safe/ethical AI coding practices. Encourage live experimentation. | Demo repository, Copilot access, prompt examples, coding standards guide | 2 hours | Global Cohort
Code Base Exploration Workshop | Facilitate guided exploration of the full stack application architecture. Encourage Pods to use Copilot to understand dependencies, APIs, and workflows. Monitor collaboration engagement. | Architecture diagrams, GitHub repository access, sandbox environment | 2–3 hours | Team
AI Test Generation Lab | Coach learners on generating unit and integration tests using Copilot. Reinforce test quality and validation practices. Provide examples of strong and weak AI-generated tests. | Test framework examples, sample prompts, IDE setup guide | 2 hours | Global Cohort
AI-Assisted Code Reviews | Facilitate structured peer code reviews in Triads or Pods. Encourage learners to evaluate readability, security, maintainability, and AI hallucination risks. | Pull request templates, review rubric, code samples | 90 min | Pod
Pair Programming Session | Rotate driver/navigator roles every 15–20 minutes. Observe collaboration dynamics and encourage effective prompting strategies. Escalate blockers as needed. | Shared coding workspace, collaboration timer, coding challenge prompts | 2 hours | Pair
Mob Programming Workshop | Moderate group-based problem solving using Mob programming techniques. Ensure all learners participate and rotate facilitation roles. | Large display/screen share, challenge backlog, facilitation checklist | 2–3 hours | Mob
Sprint Simulation | Guide Teams through agile sprint planning, AI-assisted coding, standups, and retrospectives. Reinforce engineering collaboration practices. | Jira/Azure DevOps board, sprint backlog, collaboration templates | Half day | Team
Capstone Review | Facilitate final demos and technical presentations. Evaluate AI usage effectiveness, collaboration quality, and solution outcomes. Conduct retrospective discussion. | Evaluation rubric, demo checklist, feedback forms | 2–4 hours | Regional Cohort
Reinforcement / Office Hours | Provide coaching support for applying Copilot in real-world engineering workflows. Address adoption barriers and share best practices across cohorts. | FAQ document, office hours tracker, troubleshooting guide | Weekly 60 min | Regional Cohort

## Facilitator Guides Ex 2
Session | Session Goal | Facilitator Guidance | Collaboration Structure | Materials Needed | Timing | Risks / Watchouts | Success Indicators
Kickoff Session | Establish program expectations, cohort alignment, and collaboration structures | Introduce Teams, Pods, Pairs, and Mob structures. Facilitate introductions and working agreements. Reinforce AI usage expectations and program outcomes. | Global Cohort → Teams → Pods | Kickoff deck, collaboration charter template, cohort roster, onboarding checklist | 90 min | Learner confusion on structures; unclear expectations; uneven regional participation | All learners assigned to Teams/Pods; collaboration charter completed
GitHub Copilot Foundations | Build foundational AI-assisted engineering skills | Demonstrate prompting techniques, explain AI engineering workflows, and facilitate live prompt experimentation. Encourage active participation and discussion. | Teams + Pairs | Demo repo, prompt library, Copilot licenses, IDE setup guide | 2 hours | Over-reliance on AI suggestions; learners hesitant to experiment | Learners successfully generate prompts and explain outputs
Code Base Exploration Workshop | Teach learners how to use Copilot to understand architecture and code flows | Guide Pods through repository walkthroughs. Coach learners on reading unfamiliar code and using Copilot for discovery. Encourage collaborative debugging discussions. | Pods (3–6) | Architecture diagrams, GitHub repo access, sandbox environment | 2–3 hours | Learners becoming overwhelmed by code complexity; inactive Pods | Pods produce architecture summaries and code flow documentation
AI Test Generation Lab | Develop AI-assisted testing capabilities | Coach learners on generating unit/integration tests. Review test quality, coverage, and validation techniques. Facilitate peer review of generated tests. | Pairs + Pods | Test framework examples, coding exercises, sample prompts | 2 hours | Low-quality/generated tests not validated; shallow test coverage | Teams improve test coverage and submit validated test suites
AI-Assisted Code Review Workshop | Build peer review and AI evaluation skills | Facilitate structured code reviews using PR workflows. Teach learners how to identify hallucinations, security concerns, and maintainability risks. | Triads + Pods | Pull request templates, review rubric, sample code branches | 90 min | Learners accepting AI output without critical review | PR reviews completed with actionable feedback and quality improvements
Pair Programming Session | Strengthen collaborative AI coding practices | Rotate driver/navigator roles every 15–20 minutes. Observe collaboration dynamics and intervene when participation imbalance occurs. | Pairs | Shared coding workspace, collaboration timer, challenge prompts | 2 hours | One learner dominating; weak collaboration; poor role rotation | Balanced participation and successful completion of coding tasks
Mob Programming Workshop | Develop swarm problem-solving and engineering collaboration | Moderate Mob programming sessions and rotate facilitation roles. Encourage inclusive participation and collaborative debugging/problem solving. | Mobs (5–12) | Shared IDE/screen share, challenge backlog, facilitation checklist | 2–3 hours | Dominant personalities; disengaged participants; decision bottlenecks | All learners actively contribute; working solution delivered collaboratively
Sprint Simulation | Reinforce agile delivery and AI-enabled engineering workflows | Facilitate sprint planning, standups, backlog prioritization, coding sessions, and retrospectives. Coach teams on agile collaboration behaviors. | Teams + Pods | Jira/Azure DevOps board, sprint backlog, sprint templates | Half day | Scope creep; poor coordination between Pods; sprint blockers | Sprint goals completed and retrospective identifies actionable improvements
Capstone Project Review | Evaluate technical and collaboration competency | Facilitate final demos and technical presentations. Assess AI usage effectiveness, engineering quality, and collaboration maturity. Conduct structured retrospective discussions. | Teams + Global Cohort | Evaluation rubric, demo checklist, scoring guide | 2–4 hours | Teams focusing on demos over engineering quality; uneven participation | Successful capstone delivery and demonstrated AI-assisted workflows
Reinforcement / Office Hours | Support long-term AI adoption and workflow integration | Facilitate coaching sessions and office hours. Address blockers, share best practices, and connect learners across cohorts. | Global Cohort + Regional Pods | FAQ guide, office hours tracker, troubleshooting resources | Weekly 60 min | Low post-program engagement; inconsistent adoption | Sustained Copilot usage and ongoing engineering collaboration observed

## Global Checklist
Checklist Item | Status | Owner
Regional timezone alignment | In Progress | Program Manager
Localization completed | Not Started | Program Manager
Accessibility review completed | In Progress | Curriculum Lead
Translation validated | Select... | Select...
Platform readiness confirmed | Select... | Select...
Facilitator onboarding completed | At Risk | Facilitator Lead
| Select... | Select...
| Select... | Select...

## KPIs & Dashboard
Metric | Target | Actual | % Achievement | Owner
Program Completion Rate | 85 | 92 | 108.2% | Program Manager
Learner Satisfaction Score | 85 | 96 | 112.9% | Facilitator Lead
Assessment Pass Rate | 50 | 32 | 64% | Curriculum Lead
AI Tool Adoption | 65 | 72 | 110.8% | Facilitator Lead
Code Review Quality Improvement | 35 | 36 | 102.9% | Engineering Lead
Engineering Velocity Improvement | 55 | 54 | 98.18% | Engineering Lead
Collaboration Effectiveness | 75 | 52 | 69.33% | Facilitator Lead
Select...
Select...
Select...
Select...
Select...
Select...
Total |  |  | 95.19% | 13

## Dashboard
Enterprise L&D Program Dashboard

## Dropdown Lists
List Name | Values | Included | Priority | Measurement Method | RACI | Status | MoSCoW | Responsibilities | Region | Learner Structure | Cadence | Audience | Channel | KPI Owner
Tip | Dropdowns appear when you click cells in the blue input columns on program sheets. | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select... | Select...
|  | Yes | Must Have | Assessment | R | Not Started | Must Have | Implementation | Global | Global Cohort | Kick Off | Participants | Email | L&D Lead
|  | No | Should Have | GitHub Metrics | A | In Progress | Should Have | Tech Team | NAMR | Regional Cohort | Daily | Managers | Teams/Slack | Program Manager
|  | Phase 2 | Could Have | Manager Observation | C | At Risk | Could Have | Program Delivery Team | LATAM | Team | Weekly | Executives | Zoom | Engineering Lead
|  | Optional | Won't Have | Peer Review | I | Complete | Won't Have | Curriculum Team | EMEA | Pod | Biweekly | Facilitators | Confluence | Facilitator Lead
|  | Regional Only |  | Capstone Rubric |  | Blocked |  | Facilitation Team | APAC | Mob | Monthly | Regional Leads | Jira | Curriculum Lead
|  | Pilot Only |  | Survey |  |  |  | Program Management | INDIA | Triad | Milestone-Based | Mentors | LMS | Regional Lead
|  |  |  | Dashboard KPI |  |  |  | Mentor Team | Japan | Pair | As Needed | Alumni | Live Session | Analytics Lead
|  |  |  | Mixed Methods |  |  |  |  | Other | Individual |  |  | Office Hours | Executive Sponsor
Dashboard
Manager Cascade